## Subtasks
Parent Task (existing row) | Subtask | Project | Type | Assignee | What it means | Why now / what's broken today | Files to touch | Done when | Est (h)
hub for script making | Un-hardcode the niche in the Spy sweep | AdFactory | Backend | Kamino | Turn the hardcoded category framing into a niche parameter (name, category terms, brand examples, reject rules) with a picker on the Spy page; store the niche on the sweep row. | SPY_SYSTEM_PROMPT names the 3D-shaping legging category and specific brands, so every sweep returns the same competitive set. 'Other niches' from the meeting is impossible today. | src/app/actions/spy.ts (SPY_SYSTEM_PROMPT), src/app/spy/SpyClient.tsx, new niche presets in src/lib/cellumove/ | Two different niches return visibly different brand sets, and the niche is saved on the Research row. | 3-5
| Feed ad comments into the Spy sweep | AdFactory | Backend | Kamino | After a sweep returns ads, pull the comment thread on each one (YouTube API, Reddit) and attach the top comments to the SpyAd record. | Comment mining already exists but only feeds research + excavate. The meeting asked to check comments on competitor ads; that read is manual right now. | src/app/actions/spy.ts, src/lib/youtube.ts, src/lib/reddit.ts, SpyAd interface + SpyClient render | A swept YouTube ad shows at least 5 real comments; a missing key or blown quota fails soft and the sweep still returns. | 4-6
| 'Use this idea' button on a spied ad | AdFactory | Add Feature | Kamino | Button on each spied ad that opens the new-script form with the idea, product guess and angle guess prefilled, and records the spy row as the source. | The hop from a competitor ad to a script is copy-paste today. This is exactly where the meeting said execution stalls. | SpyClient.tsx, src/app/scripts/new/page.tsx + ScriptProjectForm.tsx (query-param seeding), createScriptProject in actions/scripts.ts | Two clicks from a spied ad to a draft project, with provenance stored on the project. | 3-4
| Idea bank / swipe list for kept competitor ads | AdFactory | Add Feature | Mark | A table and page for ads you keep from sweeps: brand, hook, image, platform, source URL, note, status. 'Save to bank' from the spy grid. | Sweeps land as one-off Research rows of type competitor_spy, so nothing accumulates and a good idea from last week can't be found again. | New migration 012_idea_bank.sql, src/app/actions/spy.ts, new src/app/ideas page, src/components/nav.tsx | A saved ad survives a fresh sweep and can be filtered by niche and angle. | 5-7
| One-click 'Run through Creative Strategist' | AdFactory | Add Feature | Kamino | Paste an idea, run the strategist stage on its own, get angle candidates and hook directions back without creating a project first. | CreaStrat is step 2 of the meeting's process, but it's only reachable inside full project creation and the whole pipeline. | src/app/actions/pipeline.ts (strategist stage), a new lightweight server action, a modal on /spy or /pipeline | Idea text to strategist output in under a minute with no project row created; 'promote to project' carries the output across. | 4-6
| Make the CreaStrat prompt an editable SOP | AdFactory | Enhancement | Kamino | Move the strategist system prompt out of code into the Sop table, role-scoped, editable on /knowledge, with the current in-code text as the fallback. | Prompt tuning is where output quality actually lives, and every tweak needs a deploy today. | src/app/actions/pipeline.ts, src/lib/cellumove/agents.ts (runAgent SOP loading), knowledge/SopFoundationClient.tsx, scripts/seed-sop-foundation.ts | Editing the SOP changes the next run's output with no deploy; an empty SOP falls back to the built-in text. | 3-4
| Enforce the 5D block in the output contract | AdFactory | Enhancement | Kamino | Add avatar, angle, video format, identity level and dynamism level as required fields on the draft schema and in the prompt contract; reject drafts that omit them. | Your own generation prompt calls 5D mandatory on every script, but nothing enforces it, so drafts arrive incomplete and the gap is found late. | src/lib/cellumove/script-generation.ts (draft Zod schema, ~line 20), script-generation.server.ts prompt, ScriptStudioClient.tsx header, script-generation.test.ts | A draft missing dynamism level is rejected and retried; the 5D block renders at the top of the studio. | 3-4
| Reorder the new-project form to the stated funnel | AdFactory | Revise | Mark | Reorder the fields to Idea > Product > Angle > Avatar > Framework > Format, with the admin fields (title, creative name, ad number, strategist, editor, duration, teardown) after. | The form opens with admin metadata. The meeting's process is avatar-on-angle, then framework, then format - the form should teach that order. | src/app/scripts/new/ScriptProjectForm.tsx only - JSX order, keep the existing 'ready' validation untouched | Field order matches the process, nothing else changes, typecheck stays clean. | 1-2
| Fill out the framework library | AdFactory | Add Feature | Mark | Add reference formats beyond the five seeded (Magic Formula, Regret Arc, Behavior Change, Comparison Detox, Texture Test), each with its beats, timings and an example. | This is the '(need format)' note already on your parent row. Five frameworks means every script comes out shaped the same way. | src/lib/cellumove/reference-formats.ts (REFERENCE_FORMATS), scripts/seed-sop-foundation.ts, then rerun npm run seed:sop | New frameworks appear in the dropdown and set target duration; re-running the seed doesn't duplicate rows. Kamino supplies the beat definitions. | 3-5
| Block creation on an angle with no researched avatar | AdFactory | Enhancement | Mark | When the chosen angle has no avatars, disable submit with an explanation and a link to /research; drop the 'No specific avatar' option where avatars do exist. | Generation quality depends on the deep-dive profile. The empty option is allowed today and quietly produces generic copy nobody traces back to this. | ScriptProjectForm.tsx (the 'ready' check and avatars memo), plus a server-side guard in createScriptProject | A project can't be created on an avatar-less angle from the UI or by calling the action directly. | 1-2
Figure out modular script making | Per-module regenerate | AdFactory | Revise | Kamino | A 'regenerate this beat' control on each module with an optional instruction box; the server regenerates only that module ID and leaves the rest alone. | The studio only exposes 'AI fill all' (ScriptStudioClient.tsx:148). Modules already carry a locked flag but there's no way to redo just the hook - this is literally the 'let AI edit certain parts' row. | ScriptStudioClient.tsx, actions/scripts.ts (module-scoped variant of generateScriptProjectDraft), script-generation.server.ts | Regenerating the hook leaves every other module byte-identical and writes a ScriptEvent. | 5-7
| Regenerate hook options on demand | AdFactory | Add Feature | Mark | A 'more hooks' button that asks for a fresh set of 3-8 alternatives for the current script and appends them to the existing options. | Correction from the last version: hook options already render (ScriptStudioClient.tsx:153). The real gap is that they only ever arrive with a full draft, so more hooks means regenerating the whole script. | ScriptStudioClient.tsx, actions/scripts.ts, script-generation.server.ts (hook-only prompt path) | Pressing it adds new distinct options without touching module copy. Depends on the module-scoped path from per-module regenerate. | 3-4
| Cut the rewrite-retry cost | AdFactory | Backend | Kamino | On a validation rejection, resend only the rejected module IDs and the reason instead of re-running the whole draft prompt. | script-generation.server.ts:408 loops up to three full attempts, each a full-context Gemini call. It's the single most expensive slow path in the tool. | src/lib/cellumove/script-generation.server.ts (lines ~408-474), script-generation.ts (validation errors must carry module IDs), script-generation.test.ts | An induced single-module failure costs a fraction of the tokens; npm run test:script-generation passes. | 5-8
| Batch generate across frameworks | AdFactory | Add Feature | Kamino | From one idea, produce N drafts across the selected frameworks in a single run, returned as a comparison list. | The strategist waits on one draft at a time - the bottleneck named in the meeting. Picking from three beats waiting for one. | actions/scripts.ts, script-generation.server.ts (bounded concurrency), the /scripts list UI | Three frameworks generate concurrently and a partial failure doesn't lose the successful drafts. Land after the retry-cost fix. | 6-8
Demo Should be available by 2 Sept | Run the HANDOFF.md activation checklist | AdFactory | Backend | Mark | Run migration 003, npm run seed:sop, set Vertex creds (GOOGLE_CLOUD_PROJECT plus ADC or the service-account JSON), set Reddit OAuth and optionally YOUTUBE_API_KEY, then do one real research run and one pipeline run. | HANDOFF.md section 2: the code is in place but dormant. Nothing else on this list works end-to-end until this is done - it's the true first row. | migrations/003_avatar_profile.sql, scripts/seed-sop-foundation.ts, .env | A real sub-avatar research run persists a structured profile and a pipeline run completes; the checklist in HANDOFF.md is ticked. Kamino verifies. | 1-2
| Baseline the end-to-end time | AdFactory | Enhancement | Mark | Time and log each stage - research, strategist, draft, validation retries - plus total idea to sent-to-editor, and write the numbers into docs/. | 'Execution is slow' needs a number, both to prove the retry and concurrency work paid off and to know which stage to attack next. | src/lib/usage.ts (usage recording), ScriptEvent logging, docs/ | One table of per-stage seconds and tokens across three real runs. | 2-3
| Seed a demo dataset | AdFactory | Demo | Mark | A seed script that produces one finished example end to end: product, angle, avatar with profile, verbatims, framework, a generated script with hooks and B-roll, assigned to an editor. | So the demo doesn't hang on a live Vertex call or a missing credential, and the whole flow can be shown in three minutes. | New scripts/seed-demo.ts (follow prisma/seed.ts patterns), package.json script entry | A fresh DB plus npm run seed:demo shows a complete script in the studio with no AI call made. | 3-5
Improve performance and token efficiency on GCP | Parallelise the research and pipeline calls | AdFactory | Backend | Kamino | Run independent agent and research calls concurrently behind a bounded pool, with per-stage token budgets, instead of sequentially. | The other half of 'execution is slow'. Folds into the GCP performance row already on the sheet rather than opening a new parent. | src/app/actions/research.ts, src/app/actions/pipeline.ts, src/lib/cellumove/agents.ts | Wall clock for a full research run drops measurably against the baseline, with no rate-limit errors. | 5-8
How to use this sheet
Columns A-E match your task sheet - select B2:E19, copy, paste under the matching parent row.
Columns F-J are reference for whoever picks the task up; they are not meant to be pasted into the sheet.
Est (h) is a rough build estimate for one developer, excluding review and QA.
Suggested order: run the HANDOFF activation checklist first, then baseline the timings, then everything else.